## ITP Definitions
GTF-COR-21016 Inspection and Test Plan (ITP) Intervention Matrix Rev 0, Jun 2021
The Notification of Intervention Point Form (NOI Form) (GTF-COR-21014), available on www.technipfmc.com/suppliers, includes definitions and abbreviations for intervention points (Hold, Witness, Witness 1).
M - ‘Monitor Point’ indicates that the inspection party shall randomly inspect or verify the activity on an ad-hoc basis, commensurate with the perceived level of criticality or risk to the overall integrity of the supply scope.
R - ‘Review / Endorse point’ indicates review and / or sign off records by the nominated party as applicable.
A - ‘Approve point’ indicates that approval is required (procedures etc.) prior to the next activity being performed.
H - Hold point, W - Witness point, W1 - 1st article witness, M -Monitor Point, R - Review / Endorse point, A - Approve point
ITP Matrix does not contain an exhaustive list of manufacture activities, supplier is responsible to include any activities not captured on ITP Matrix within SUPPLIER and SUB-SUPPLIER(s) provided ITP.
Please note intervention points may be amended during document review / approval.

## Linepipe
|  |  | LinePipe - |  |  |  |  | H - Hold point, W - Witness point, W1 - 1st article witness, M -Monitor Point, R - Review / Endorse point, A - Approve point
ACTIVITY | Document Approval (List Documents) | Pre-Prodcution Meeting (PPM) | Incoming Material inspection / Verfy Material Certification | Verify Equipment Calibration | Consumable Storage | Steel Making - Melting Of Scrap In Furnace | Manufacture Procedure Qualification (MPQT) | Steel Making - Ladle analysis | Steel Making - Production Of Pipe Billets | Stamping / Identification Of Billets | Rolling Of Billets | Piercing Of Billets | Post Pierce Rollig | Sizing | End Cropping | Stencilling / Transfer of Billet ID | Welding | NDE (list Appliccable, VI, MPI, LPI, UT, RT etc..) | Test Sampling | Mechanical Testing | Metallographic test | Visual Inspection | Dimentional / Out of Roundness / Straightness / Squareness / Wall thickness | Pipe Straightening | Heat Treatment | End Preperation | Pressure Test | Residual magnetism | Weighing | NCR Closure | Final Inspection | Packing / Protection Inspection | Load out | As-Built
SCOPE OF SUPPLY
LinePipe Criticality A & B | A | H | M | M | M | W1 | W | W1 | W1 | W1 / R | W1 | W1 | W1 | W1 | W1 | W1 | W1 | W1 | W | W | W | W1 | W1 | W1 | W1 | W1 | W1 | W1 | W1 | A | H | W1 | W | A
LinePipe Criticality C & D | A | H | M | M | M | M | W | M | M | M | M | M | M | M | M | M | M | M | W | W | W | W1 | W1 | M | M | M | W1 | M | W1 | A | W | W1 | W | A

## Bending
|  |  | Pipe Bending |  |  | H - Hold point, W - Witness point, W1 - 1st article witness, M -Monitor Point, R - Review / Endorse point, A - Approve point
ACTIVITY | Document Approval (List Documents) | Pre-Prodcution Meeting (PPM) | Incoming Material inspection / Verfy Material Certification | Verify Equipment Calibration | Consumable Storage | Qualifcation Bending | Qualifcation Bending - Post-bend heat treatment | Qualifcation Bending - Surface cleaning | Qualifcation Bending - Dimensional survey | Qualifcation Bending - NDT (Please list applicable method(s) i.e MPI / PMI / UT / Etc…) | Qualification Mechanical Test (Please detail tests) | Production bending | Post-bend heat treatment | Production mechanical testing | Surface cleaning | Cut to length & machine bevel | NDT (Please list applicable method(s) i.e MPI / PMI / UT / Etc…) | identification marking | Dimentional Survey Check | Through Bore Gauging | NCR CLOSURE | Final Inspection Release | Packing Inspection | As-Built Submission
SCOPE OF SUPPLY
Pipe Bending Criticality A / B Supply ** | A | H | R | M | M | W | W1 | M | W | W | W | W1 | W1 | W | M | W1 | W1 | M | W | W | A | H | W | A
Pipe Bending Criticality C / D Supply ** | A | H | R | M | M | W | W1 | M | W | W | W | M | M | M | M | M | M | M | W1 | W1 | A | W | W | A
** Criticality based on line pipe application criticality

## Fab & Spools
|  | General Fabrication & Spool Fabrication |  |  |  |  | H - Hold point, W - Witness point, W1 - 1st article witness, M -Monitor Point, R - Review / Endorse point, A - Approve point
ACTIVITY | Document Approval (List Documents) | Pre-Prodcution Meeting (PPM) | Incoming Material inspection / Verfy Material Certification | Verify Equipment Calibration | Consumable Storage | Weld Procedure Qualification | Mechanical Test (please list / Detail) - See Mech Test Tab.. | NDT | Welder Qualification | Material Cutting | Tack weld fabrication set up | Spool Butt weld set up (bevel check as per WPS) | Pre-weld dimentional check | Pre-Heat check | Welding operations | Weld monotoring | Weld visual inspection | NDE (list Appliccable, VI, MPI, LPI, UT, RT etc..) | Review of NDT reports | Weld repair (as per R-WPS) | NDT Following repair (List Applicable (VI, MPI, LPI, UT, TR Etc..) | Review of NDT reports follwing repair | Dimentional Check | Load Testing - Procedure Required | Trial Lifts - Proceudure required | Pressure test - Procedure Required | Bolt tensioning - Procedure required | Coating - Separate ITP to be provided | NCR Closure | Final Inspection | Packing Inspetion
Scope of Supply
Structual Fabrication Criticality A & B | A | H / RW | R / A | M / R | M / R | W / A | W | W1 | W | M | W1 | N/A | W1 | W1 | W1 | W1 | W1 | W1 | R | H | W | R | W | W | W | W | W1 | W | A | H | W
Structual Fabrication Criticality C & D | R | N/A / RW | M / R | M | M | M | M | M | M | M | M | N/A | M | M | M | M | M | M | M / R | H | M | R | W | W | W | W | W1 | M / R | R | H | W
Pipeline / Spool Fabrication Criticality A & B | A | H / RW | R/A | M | M | W | W | W1 | W | M | N/A | W1 | W1 | W1 | W1 | W1 | W1 | W1 | R / A | H | W | R / A | W | N/A | W | W | W1 | W | A | H | W
Pipeline / Spool Fabrication Criticality C & D | R | N/A / RW | M/R | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M R | H | M | R | M | N/A | W | W | M | M | R | H | W

## Struc Coating
| Coating | [6 empty] | H - Hold point, W - Witness point, W1 - 1st article witness, M -Monitor Point, R - Review / Endorse point, A - Approve point
ACTIVITY | Document Approval (List Documents) | Pre-Prodcution Meeting (PPM) | Incoming Material inspection / Verfy Material Certification | Verify Equipment Calibration | Personnel qualification | Consumable Data sheets & Storage | Surface Preperation Visual | Degreasing/Cleaning & Drying | Blast / Cleaning | Environmental condition Verification | Grade of cleanliness SA .. | Surface Roughness / Visual Inspection | Surface visual inspection after blasting | Dust level after blasting | Surface salt test (Chloride test) | PAINTING APPLICATION - Enviromental verification | Masking of unpainted areas | Wet film thickness | Dry film thickness | Visual inspection | REPAIR OF PAINTING (If any) | HOLIDAY TESTING | Production test coupon | Test for Adhesion (Pull-off test) | Checking of the RAL Colour | Final visual inspection | NCR Closure | RELEASE | As-Built Submission
Scope of Supply
Coating of Criticality A & B Items | A | H | W | W | R | R/W | W1 | W1 | W1 | W1 | W1 | W1 | W1 | W1 | W1 | W1 | W1 | W1 | W1 | W1 | H | W1 | W1 | W1 | W1 | W | A | H | A
Coating of Criticality C & D Items | R | H | M | M | M | R/M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | H | M | M | M | M | W | R | H | A

## Valve
|  |  | Subsea Valves |  |  |  | H - Hold point, W - Witness point, W1 - 1st article witness, M -Monitor Point, R - Review / Endorse point, A - Approve point
ACTIVITY | Document Approval (List Documents) | Pre-Prodcution Meeting (PPM) | Incoming Material inspection / Verfy Material Certification | Verify Equipment Calibration | Consumable Storage | Forging Activity - Chemical analysis check of mill certificate | Forging Activity - Forging | Forging Activity - Machining before heat treatment | Forging Activity - Heat treatment (solution annealing) | Forging Activity - Test coupon identification | Forging Activity - Mechanical tests | Forging Activity - Metallographic Examination ( Corrosion, Ferrite, Austenite spacing ..) | Forging Activity - Visual & dimensional exam | Forging Activity - NDT (Please list applicable method(s) i.e MPI / DPI / PMI / UT / Etc…) | Production - Rough machining prior of Cladding | Production - Visual Check | Hardness Test | Production - Dimentional Check | Production - NDT (Please list applicable method(s) i.e MPI / DPI / PMI / UT / Etc…) | Overlay Welding | PMI on Overlay | Measurement of overlay thickness | Machining | NDT (Please list applicable method(s) i.e MPI / DPI / PMI / UT / Etc…) | Weld Repair | Final Machining | Visual Check | Dimentional Check | NDT (Please list applicable method(s) i.e MPI / DPI / PMI / UT / Etc…) | Tungsten Carbide Coating | Hardfacing | ASSEMBLY - PMI of parts before assembly | ASSEMBLY - Traceability verification of main parts | ASSEMBLY - Visual check of parts | ASSEMBLY - Alcohol Test | ASSEMBLY - Valve Assembly | ASSEMBLY - Bolt tightening control | ASSEMBLY - fluid compensation filling | ASSEMBLY - Dimensional check of valve assembly | FAT - NDE completed - verification of reports | FAT sequence according to approved procedure | MARKING AND PAINTING | Valve assembly weighting | Final Inspection Checklist | Mechanical Completion Check Record (MCCR) | NCR Closure | Final Inspection Release | Packing Inspection | As-Built Submission
SCOPE OF SUPPLY
Criticality A & B Valve Manufacture | A | H | M / A | M | M | R | W1 | W1 | W1 | W | W | W | W1 | W1 | M | W1 | W1 | W1 | W1 | W1 | W1 | W1 | M | W1 | H | M | W1 | W1 | W1 | R | W1 | W1 | M | M | M | M | W1 | W1 | W1 | W / R | W | W1 | W1 | W | W | A | H | W | A
Criticality C & D Valve Manufacture | A | H | M / A | M | M | R | M | M | M | W | W | W | W1 | M | M | M | M | M | M | M | M | M | M | M | H | M | M | M | M | R | M | M | M | M | M | M | M | M | M | R | W | M | M | W | W | A | H | W | A
NOTES- ITP to include: - Chemical Analysis table - Test Sampling location drawing, - Test sampling table - Type of test, number of tests, and test locations - Mechanical & Metallographic Test steps detailed within ITP or separate ITP to be provided.

## Flanges
|  |  | Flanges | [10 empty] | H - Hold point, W - Witness point, W1 - 1st article witness, M -Monitor Point, R - Review / Endorse point, A - Approve point
ACTIVITY | Document Approval (List Documents) | Pre-Production Meeting (PPM) | Incoming Material inspection / Verify Material Certification | Verify Equipment Calibration | Consumable Storage | CHEMICAL / LADLE ANALYSIS | CUTTING OF BASE MATERIAL | FORGING | PRE-MACHINING INSPECTION | HEAT TREATMENT - LOADING / FURNACE CALIBRATION | HEAT TREATMENT - QUENCH TEMP… | HEAT TREATMENT - TEMPERING | COOLING - TEMP… | HARDNESS CHECK | ULTRASONIC EXAMINATION | TEST SAMPLING | PRODUCT CHEMICAL ANALYSIS | MECHANICAL TEST - LIST ALL AND ACCEPTANCE CRITERIA | MACHINING BEFORE WELDING | WELD OVERLAY SURFACE | WELD REPAIR | WELDING | WELD REPAIR | NDT - LIST ALL APPLICABLE - VI, MPI, DPI, PMI, Cladd Thickness, Hardness etc.. | FINAL MACHINING | HYDRO-TEST | VISUAL DIMENSIONAL CHECK | MARKING | DISPATCH DOSSIER | NCR CLOSURE | FINAL INSPECTION (IRC) | PACKING INSPECTION | MRB REVIEW
SCOPE OF SUPPLY
Flange - CRITICALITY A & B | R / A | H | M / R / A | M | M | R | R | W1 | M | W1/ R | W1/ R | W1/ R | R | W1 | W1 | W1 | W1 | W1 | W1 | W1 | H | W1 | H | W1 | M | W1 | W | W1 | R | A | H | W | R/A
Flange - CRITICALITY C & D | R | H | R | M | M | R | M | M | M | M | M | M | M | M | M | M | M | M | M | M | H | M | H | M | M | W1 | W1 | W1 | R | A | H | W | R/A
NOTES- Forging ITP to include: - Chemical Analysis table - Test Sampling location drawing, - Test sampling table - Type of test, number of tests, and test locations - Mechanical Test steps detailed within ITP or separate ITP to be provided.

## Fittings
|  |  | Fittings (Elbow / Tee's …) | [10 empty] | H - Hold point, W - Witness point, W1 - 1st article witness, M -Monitor Point, R - Review / Endorse point, A - Approve point
ACTIVITY | Document Approval (List Documents) | Pre-Production Meeting (PPM) | Incoming Material inspection / Verify Material Certification | Verify Equipment Calibration | Consumable Storage | CHEMICAL / LADLE ANALYSIS | CUTTING OF BASE MATERIAL | FORGING | PRE-MACHINING INSPECTION | HEAT TREATMENT - LOADING / FURNACE CALIBRATION | HEAT TREATMENT - QUENCH TEMP… | HEAT TREATMENT - TEMPERING | COOLING - TEMP… | HARDNESS CHECK | ULTRASONIC EXAMINATION | TEST SAMPLING | PRODUCT CHEMICAL ANALYSIS | MECHANICAL TEST - LIST ALL AND ACCEPTANCE CRITERIA | MACHINING BEFORE WELDING | WELD OVERLAY SURFACE | WELD REPAIR | WELDING | WELD REPAIR | NDT - LIST ALL APPLICABLE - VI, MPI, DPI, PMI, Cladd Thickness, Hardness etc.. | FINAL MACHINING | HYDRO-TEST | VISUAL DIMENSIONAL CHECK | MARKING | DISPATCH DOSSIER | NCR CLOSURE | FINAL INSPECTION (IRC) | PACKING INSPECTION | MRB REVIEW
SCOPE OF SUPPLY
Forming CRITICALITY A & B | R / A | H / RW | M / R / A | M | M | R | R | W1 | M | W1 / R | W1 / R | W1 / R | R | W1 | W1 | W1 | W1 | W | M | W1 | H | W1 | H | W1 | M | W1 | W | W1 | R | A | H | W | R/A
Forming CRITICALITY C & D | R | RW | R | M | M | R | M | M | M | M | M | M | M | M | M | M | M | M | M | M | H | M | H | M | M | WP | WP | WP | R | A | H | W | R/A
NOTES- Forging ITP to include: - Chemical Analysis table - Test Sampling location drawing, - Test sampling table - Type of test, number of tests, and test locations - Mechanical Test steps detailed within ITP or separate ITP to be provided.

## Anode
|  |  | Anode Manufacture |  |  |  | H - Hold point, W - Witness point, W1 - 1st article witness, M -Monitor Point, R - Review / Endorse point, A - Approve point
ACTIVITY | Document Approval (List Documents) | Pre-Prodcution Meeting (PPM) | Incoming Material inspection / Verfy Material Certification | Verify Equipment Calibration | Consumable Storage | Incoming Material Chemical Compasition | Incoming Material Visual Check | Pre Qualification Testing | Pre Qualification Testing - Insert Blast | Pre Qualification Testing - Insert Weight | Pre Qualification Testing - Insert Dimention check | Pre Qualification Testing - Sample for chemical composition analysis | Pre Qualification Testing - Chemical Analysis | Pre Qualification Testing - Visual Inspection | Pre Qualification Testing - Weight Check | Pre Qualification Testing - Destructive Testing | Pre Qualification Testing - Dimentional Check | Pre Qualification Testing - Dimentional Check | Pre Qualification Testing - Fit up test | Insert Fabrication | Insert Blasting | Insert Weight Check | Chemical Composition Analysis | Electrochemical Capacity / Potential Test | Electrical Resistance Test | Visual Inspection | Anpde Weight Check | Destructive Test | Dimentional Check | Anode Coating | Anode Marking | Fit Up Test | Pull Test (Cable Traction Resistance) | NCR Closure | Final Inspection Release | Packing | As-Built Submision
SCOPE OF SUPPLY
Anode | A | H | R | R | M | M | M | W1 / A | W1 | W1 | W1 | W1 | W1 | W1 | W1 | W1 | W1 | W1 | W1 | M | M | W1 | W1 | W1 | W1 | W1 | W1 | W1 | W1 | M | M | W1 | W1 | A | H | W | A

## Gasket
|  |  | Gaskets |  |  |  | H - Hold point, W - Witness point, W1 - 1st article witness, M -Monitor Point, R - Review / Endorse point, A - Approve point
ACTIVITY | Document Approval (List Documents) | Pre-Prodcution Meeting (PPM) | Incoming Material inspection / Verfy Material Certification | Verify Equipment Calibration | Consumable Storage | Receipt/Inspection & Verify Material Composition | Hardness Testing | Manufacture Ring Joint Gasket | NDT - LIST ALL APPLICABLE - VI, MPI, DPI, PMI, Cladd Thickness, Hardness etc.. | Marking/ Tagging & Colour Coding N/A | NCR Closure | Final Inspection Release | Packing Inspection | As-Built Submission
SCOPE OF SUPPLY
Gasket Supply | A | H | R | M | M | R | M / R | M | M / R | R | A | H | W | A

## Nuts & Bolts
|  |  | Bolts / Studbolts and Nuts |  |  |  | H - Hold point, W - Witness point, W1 - 1st article witness, M -Monitor Point, R - Review / Endorse point, A - Approve point
ACTIVITY | Document Approval (List Documents) | Pre-Prodcution Meeting (PPM) | Incoming Material inspection / Verfy Material Certification | Verify Equipment Calibration | Storage | Thread Roll Bar | Cut / Chamfer | Stamp | Inspect / Dimentions | Mechanical Testing Preperation | Heat Treatment | Mechanical Testing - State activities (i.e Tensile, Imact, hardness, PMI, Proof) | NDT - LIST ALL APPLICABLE - VI, MPI, DPI, PMI, Cladd Thickness, Hardness etc.. | Coat / Plate | Assemble | Final Inspection Release | NCR Closure | Packing Inspection | As-Built Submission
SCOPE OF SUPPLY
Bolts / Studbolts and Nuts | A | H | R | M | M | M | M | M | M | M | M | M | M | M | M | H | A | W | A