## SMDR
Supplier name |  |  |  |  | TechnipFMC project name
TechnipFMC's Supplier no. |  |  |  |  | TechnipFMC project no.
Supplier order no. |  |  |  |  | Product type (short description)
Supplier SMDR contact |  |  |  |  | TechnipFMC part no. from PO line
TechnipFMC purchase order no.
SIR ref. no. | Supplier doc. |  | Voided date | TechnipFMC part no. "level where used" | Document title | Submission date |  | Review / Info / As Built |  | Approval Status
| No. | Rev. |  |  |  | Plan | Actual | TechnipFMC | Client | Rev. | Code
Supplier Documentation Requirements (SDR)
101 |  |  |  | All (as heading) | SMDR | DD.MM.YY | DD.MM.YY | R
Manufacturing Information Requirements (MIR)
237
Supplier's comments/remarks
DELETE THIS SECTION BEFORE SUBMITTING
This template shall be used by Supplier when manual SMDR is instructed in the Purchase Order. Instructions for use of this template are available in the 'Instructions' tab. This document is available for Suppliers through www.technipfmc.com/en/services/suppliers/documents-and-templates and for TechnipFMC personnel in SAP with document number LIST-0000023456,rev. S | [9 empty] | Click here for instructions
Click here for template

## Instructions
LIST-0000023456, rev. S | Delete all tabs except SMDR tab from the file before submitting it to TechnipFMC
SMDR - supplier Master Document Register is a register that summarizes which Pre-manufacturing documents shall be reviewed and approved by TFMC (and Client when required) for part numbers. The SMDR is used to plan and track submission of Supplier documents and to show status. This instruction is intended for Suppliers to TechnipFMC when header text of a PO indicate use of Manual SMDR. It specifies how the manual SMDR shall be prepared, submitted and maintained. Documentation requirements (format and content) are described in engineering specifications linked to the TechnipFMC Part Report (DBI) at each level in the assembly Bill of Material (BOM). The requirements are summarized in document BOMs as SDR which are linked to the engineering specifications. These SDR BOMs are made up of Supplier Information Requirements (SIRs) which are a code number and a short title which briefly describes the intention of the information requirement.
Specific requirements | Description
How to identify | Review the document requirements in the Part Report and/or the PO, and identify the relevant document types (SIR) to record documents to the SDR section in the SMDR. The manual SMDR (SIR101) itself is regarded as any other revision controlled document, and shall be reviewed and accepted by TechnipFMC.
Administrative | The requirements related to document language, revision management, and review timeframes are specified in PRD-0000035686, Administration Requirements: Document Management.
For Manufacturing Record Book, SIR237, please review GSD-21-0004 PURCHASE ADMINISTRATIVE REQUIREMENTS – QUALITY MANAGEMENT.
Supplier shall use the latest revision of FMC's template for the SMDR. The template shall not be modified, except for adding/removing rows when required (not columns). The SMDR document shall be submitted as 2 files, the original spreadsheet (Microsoft Excel) and PDF format. Not as a scanned PDF, but generated from the original spreadsheet.
Principles | Supplier shall use the latest revision of a document if not otherwise is instructed: • Ensure that the latest revision is submitted to TechnipFMC. • Ensure that the latest revision is accepted by TechnipFMC. If TechnipFMC rejects (code 3) or return a document with comments (code 2), Supplier shall evaluate if the required changes should lead to a new revision or a new document number.
Dates | Date format shall be 3x2 digits, like this; DD.MM.YY. E.g. 23.11.12 for November 23, 2012.
Revision of the SMDR | New revision is required: • When documents are added. • When documents are voided. - Void means "first listed, but not going to be used". - Voided documents shall remain listed for reference. • Together with a new document, but not for new revisions of already listed documents. • When Plan submission dates are changed. • When all the listed documents obtained Approval Status Code 1, SMDR to be sent for final/As Built. In this final revision of SMDR, all the documents shall be listed with latest revisions which have been used for the PO mentioned in heading. - Except for the MRB, since the MRB shall contain this revision of the SMDR. New revision is not required when there are: • Changes only in revisions of the listed documents. • Changes only in Approval Status Codes of the listed documents. Not every revision of the SMDR shall be submitted to TechnipFMC. Supplier shall immediately update the SMDR with appropriate code in the column 'Approval Status Code'. Supplier shall always have an updated SMDR in their document management system.
Change | To track the changes from one submitted revision of the SMDR to the next, Supplier shall: 1. Mark all new changes with one color (either the text itself or the cell). 2. Remove this marking immediately after the revision is submitted to TechnipFMC.
Acronym | Meaning
SMDR | Supplier Master Document Register
SIR | Supplier Information Requirement
SDR | Supplier Documentation Requirement
MIR | Manufacturing Information Requirement
DRL | Document Requirement List
PO | Purchase Order
LIST-0000023456 rev Q
Column name | Description
Supplier name | Supplier's company name, as stated on the Purchase Order (PO) PDF print. If company name is wrong in the PO, then notify TechnipFMC.
TechnipFMC's Supplier no. | Supplier's identification number in the TechnipFMC system. Stated on the PO PDF print.
Supplier order no. | Supplier's own order/production number, for convenience. Not a requirement.
Supplier SMDR contact | Contact person for this SMDR at Supplier, for TechnipFMC's convenience in case of questions.
TechnipFMC purchase order no. | TechnipFMC's PO number as stated on the PO pdf print (and in Ariba).
TechnipFMC project name | List TechnipFMC's project name if stated in the PO. Leave blank if not stated in PO.
TechnipFMC project no. | List TechnipFMC's project number if stated in the PO. Leave blank if not stated in PO.
Product type (short description) | Short/generic description of the type of the products (types of products) that this SMDR cover.
TechnipFMC part no. from PO line | The part number(s) specified in the PO, which is the procured level, that this SMDR cover.
SIR ref. no. | SIR reference number. Identified by the SDR/MIR link in the heading of the Part Report.
Supplier doc. ¦ No. | • Documents shall be registered/managed in Supplier's own document management system. • Documents shall have unique document numbers. • Document numbers shall not exceed 25 alphanumeric characters. • Revision number shall not be a part of the document number. • Listed on the SMDR, the document number must be exactly as in the document itself.
Supplier doc. ¦ Rev. | • All documents shall have revision characters/digits, max. 4 characters/digits. • All documents shall receive new revision characters/digits when revised/changed. • Listed on the SMDR, the revision level must be exactly as in the document itself.
Voided date | When a document is initially listed, but for some reason shall not be used, then Supplier shall not remove - but mark the document as voided. To void, fill in the actual date in 'Voided date' column. It is recommended to change the color of the voided line to grey. Example: Supplier replacing one document with another in a new revision of a SMDR, must void existing line and add new line with correct information.
TechnipFMC part no. "level where used" | The appropriate part number level to which the document is relevant: • When a sub-component part(s) to an assembly is relevant to a listed document, then the specific sub-component part number(s) shall be specified. • If all the parts mentioned in the heading ‘TechnipFMC part no. from PO line’ is relevant for a listed document, then the text “All (as heading)” applies.
Document title | Listed on the SMDR, the document title must be exactly as in the document itself.
Submission date ¦ Plan | Date Supplier intends to submit the document to TechnipFMC. Mandatory in first revision of SMDR for all listed documents (which have not been submitted earlier). Exception: For re-use documents, the 'Plan' column does not to be completed.
Submission date ¦ Actual | Date Supplier actually did submit the listed revision of the document to TechnipFMC.
Review / Info / As Built ¦ TechnipFMC | Supplier shall list all documents for review “R” with following exceptions: Exceptions: • If Supplier uses TechnipFMC procedures (e.g. Q specifications), those shall be listed in the SMDR and marked for information “I”. (For Welding SIRs, supplier shall combine WPS and related WPQR(s) in to one .pdf file and list it as one document number in the SMDR)
Review / Info / As Built ¦ Client | TechnipFMC will inform Supplier which documents shall be listed for review “R” and information “I” in the 'Client' column.
Approval Status | For the first revision of a SMDR for a PO, the 'Approval Status' columns shall be: • Left blank for new documents submitted/issued to TechnipFMC. • Filled in with 'Approval Status Code' for the listed documents if the part number is a repeat order.
Approval Status ¦ Rev. | The last reviewed revision shall be listed.
Approval Status ¦ Code | Documents/drawings not pre-approved by TechnipFMC will be returned to Supplier with a status code indicating approval or rejection. Comments for incorporation will be communicated when applicable. 1 - Accepted 2 - Accepted with comments incorporated. Revise and resubmit. 3 - Rejected.
Supplier's comments/remarks | Additional comments/remarks can be used by Supplier to prevent misunderstandings by TechnipFMC during the review.
Example: Illustrates new revisions, voiding, change tracking, and MRB for manufacturing documents

## Change Log
LIST-0000023456 |  | Delete this 'Change Log' tab from the file before submitting it to TechnipFMC
Rev | Date | Summary of changes
S | 2024-11-11 | Purpose section added and links to administrative documents. Removed Coating (line 36) New example SMDR. Removed reference to DRL. Updated Approval Status Code wording.
R | 2019-10-24 | SMDR Template :Removed column DR.doc.no (column M) Instructions : Updated info regarding how to fill in Approval Status code Column
Q | 2019-10-09 | Clarifications to Instructions (Doc title, Submission plan, Review/Info/As Built, Approval status, Requirement for SMDR revision)
P | 2018-06-16 | Instructions moved from word format into worksheet in excel
## | ## | For previous versions, see change log in Word document